## sprints
Feature | Android Controller | Combat | Enemies | Puzzles | Power ups | Maze | Movement
What is it? | Allow user to use an android controller to control player. Attacks such as shaking the controller. | Melee combat. Ranged combat also availble. Attack strength will be determined by the players level | Varies of enemies that patrol the player and attack the enemy. | End level puzzles to progress. - Fix the pattern - movement sliding | Power ups the player can pick up. Such as improved visibility,invincibility , increased health. | Players to traverse the maze to complete the level | How each GameCharacter will move.
Sprint 1 | research | implement combat based on class diagram(4hr) | implement enemy based on class diagram(2hr) | implement puzzle class as per diagram (2hrs) | implement power ups as per diagram(2hrs) | Print to screen(4hr) | implement movement based on class diagram(2hr)
Sprint 2 | research | design pseudocode | design pseudocode for methods that aren't inherited | design pseudocode for 1 puzzle | design pseudocode for visibility power up |  | Player/enemy movement(5hrs)
Sprint 3 |  |  | Create enemy movement behavior(5hrs) |  | health increase(1hr) invincibility(1hr) attack increase(2hrs) vision increase(2hrs)
Sprint 4 |  |  | Create second enemy type(3hrs)
Sprint 5 |  |  |  | Puzzle type 1- Match the colours(5hrs)
Sprint 6 |  |  |  | Puzzle type 2 - sliding ice (6hrs)
Sprint 7 | [5 empty] | Maze collsion(6hr)
Sprint 8 | [5 empty] | Creating level deisgn(5hrs)
Sprint 9 | [5 empty] | placing enemy,player,puzzles into level
Sprint 10 | connecting to android (8hrs)
Sprint 11 | Mapping android controls to player movement and actions
Sprint 12 | Additional features/quality of life improcements
Sprint 13 | Additional features/quality of life improcements
Sprint 14 | Additional features/quality of life improcements
Sprint 15 | Additional features/quality of life improcements

## fbs
Feature | Android Controller | Combat | Enemies | Puzzles | Power ups | Maze | Player
What is it? | Allow user to use an android controller to control player. Attacks such as shaking the controller. | Melee combat. Ranged combat also availble. Attack strength will be determined by the players level | Varies of enemies that patrol the player and attack the enemy. | End level puzzles to progress. - Fix the pattern - movement sliding | Power ups the player can pick up. Such as improved visibility,invincibility , increased health. | Forcing players to traverse the maze to complete the level | The main protagonist of the games, The main perspective of gamers in the game.
| connecting to android | detect enemy in attack area | detect player in attack area | Switch Puzzle-Each switch changes a colour | Item placement in level | Get designs for each levels | Player sprites
| take information from sensors | detect collision | make enemy attack | Ice puzzle-Sliding | Item collision |  | Player behaviour
| create input buttons | Enemy reaction | deal damage | Riddles Puzzele | power up types | enable pixel perfect collision detection for each maze | Player movement
| assign function of each button | Enemy attack | enemy sprites |  | Shield |  | Player combat
|  | Ranged weapon | enemy types |  | Armour |  | Player interactions
|  |  | Behaviour |  | Torch | make a random selection of mazes | Player stats
Sword
Health Potion
Invincibilty item